## Project Schedule with Timeline
SCHEDULE PROJECT TIMELINE
|  | Company Name | [6 empty] | High-Performance Computing Cluster
|  | Project Name | [6 empty] | Enhancing Legal Assistance using HPCC systems
|  | Project Start | [6 empty] | 2024-01-10
Display Week | 1
Task
| 2024-01-08 | 2024-01-09 | 2024-01-10 | 2024-01-11 | 2024-01-12 | 2024-01-13 | 2024-01-14 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-01-18 | 2024-01-19 | 2024-01-20 | 2024-01-21 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-25 | 2024-01-26 | 2024-01-27 | 2024-01-28 | 2024-01-29 | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-02 | 2024-02-03 | 2024-02-04
Phase 1
Exploring HPCC systems
Exploring HPCC systems
Exploring HPCC systems
Exploring HPCC systems
Phase 2
Finding NLP model to extract key words
Searching for relevant datsets to suit our needs
Spray the dataset onto HPCC cluster and develop demo roxie query
Phase 3
Creating a web interface for interaction
Implementing searching algortihm to match keywords
Sending Kewords to HPCC cluster using ROXIE query
Meeting a lawyer to get input about the product and corrections
Phase 4
Starting with research paper
Improvements on keyword extraction and UI of website
Development of index searching for quicker response time
Improvements on Roxie Query to get accurate and quicker results
Task | 2024-01-12: Assign To; 2024-01-19: Start; 2024-01-23: Days; 2024-01-27: End; 2024-01-31: Status
Phase 1 | bar: 2024-01-08 to 2024-01-12; 2024-01-19; 2024-01-23; 2024-01-27; 2024-01-31
Exploring HPCC systems | 2024-01-12: Nihar Mandahas; 2024-01-19: 2024-01-10; 2024-01-23: 20; 2024-01-27: 2024-01-30; 2024-01-31: Complete
Exploring HPCC systems | 2024-01-12: Pratheek Rao, Manvith L B; 2024-01-19: 2024-01-10; 2024-01-23: 20; 2024-01-27: 2024-01-30; 2024-01-31: Complete
Exploring HPCC systems | 2024-01-12: Skanda P R; 2024-01-19: 2024-01-10; 2024-01-23: 20; 2024-01-27: 2024-01-30; 2024-01-31: Complete
Exploring HPCC systems | 2024-01-12: Arya Hariharan; 2024-01-19: 2024-01-10; 2024-01-23: 20; 2024-01-27: 2024-01-30; 2024-01-31: Complete
Phase 2 | bar: 2024-01-08 to 2024-01-12; 2024-01-19; 2024-01-23; 2024-01-27; 2024-01-31
Finding NLP model to extract key words | 2024-01-12: Nihar Mandahas, Arya Hariharan; 2024-01-19: 2024-01-30; 2024-01-23: 20; 2024-01-27: 2024-02-19; 2024-01-31: Complete
Searching for relevant datsets to suit our needs | 2024-01-12: Pratheek Rao, Manvith L B; 2024-01-19: 2024-01-30; 2024-01-23: 5; 2024-01-27: 2024-02-04; 2024-01-31: Complete
Spray the dataset onto HPCC cluster and develop demo roxie query | 2024-01-12: Skanda P R; 2024-01-19: 2024-01-30; 2024-01-23: 3; 2024-01-27: 2024-02-02; 2024-01-31: Complete
Phase 3 | bar: 2024-01-08 to 2024-01-12; 2024-01-19; 2024-01-23; 2024-01-27; 2024-01-31
Creating a web interface for interaction | 2024-01-12: Manvith; 2024-01-19: 2024-02-20; 2024-01-23: 15; 2024-01-27: 2024-03-06; 2024-01-31: Complete
Implementing searching algortihm to match keywords | 2024-01-12: Skanda P R; 2024-01-19: 2024-02-13; 2024-01-23: 30; 2024-01-27: 2024-03-14; 2024-01-31: Complete
Sending Kewords to HPCC cluster using ROXIE query | 2024-01-12: Manvith; 2024-01-19: 2024-02-28; 2024-01-23: 30; 2024-01-27: 2024-03-29; 2024-01-31: Complete
Meeting a lawyer to get input about the product and corrections | 2024-01-12: Nihar Mandahas, Arya Hariharan , Manvith LB , Pratheek Rao and Skanda PR; 2024-01-19: 5/14/24; 2024-01-23: 1; 2024-01-27: 5/14/24; 2024-01-31: Complete
Phase 4 | bar: 2024-01-08 to 2024-01-12; 2024-01-19; 2024-01-23; 2024-01-27; 2024-01-31
Starting with research paper | 2024-01-12: Nihar Mandahas, Arya Hariharan , Manvith LB , Pratheek Rao and Skanda PR; 2024-01-19: 2024-05-20; 2024-01-27: 2024-05-20; 2024-01-31: In Progress
Improvements on keyword extraction and UI of website | 2024-01-12: Manvith; 2024-01-19: 2024-05-14; 2024-01-23: 15; 2024-01-27: 2024-05-29; 2024-01-31: Complete
Development of index searching for quicker response time | 2024-01-12: Skanda P R; 2024-01-19: 2024-05-15; 2024-01-23: 5; 2024-01-27: 2024-05-20; 2024-01-31: Complete
Improvements on Roxie Query to get accurate and quicker results | 2024-01-12: Skanda P R, Pratheek Rao; 2024-01-19: 2024-05-19; 2024-01-23: 5; 2024-01-27: 2024-05-24; 2024-01-31: In Progress
Phase 5 | bar: 2024-01-08 to 2024-01-12; 2024-01-19; 2024-01-23; 2024-01-27; 2024-01-31
[12 empty] | 2024-02-13 |  |  |  | 2 |  |  |  | 2024-02-15 |  |  |  | Not Started
[12 empty] | 2024-02-16 |  |  |  | 2 |  |  |  | 2024-02-18 |  |  |  | Not Started
[12 empty] | 2024-02-19 |  |  |  | 2 |  |  |  | 2024-02-21 |  |  |  | Not Started
[12 empty] | 2024-02-22 |  |  |  | 2 |  |  |  | 2024-02-24 |  |  |  | Not Started